## Slide 1: Hockey Stadium Project
Presented By: Sijan Dahal & Yaman Pandey
Group 4
Date: Nov. 25, 2024
MET-625, Advance Project Management

## Slide 2
Project Name
Budget
Project Goal
Construct a 5000 seated hockey stadium in MNSU
following all the university codes.
Gives Chance for Mavericks team to host the game
Boosts internal tourism in Mankato.
Gives oppurtunity for local players.
To build a 5,000-seated stadium at Minnesota State University, Mankato. The stadium would consist of Locker Rooms for both male and female players and an indoor training facility for the home team to train in during the off-season.
Yaman Pandey/ Sijan Dahal
Pictures
Project Scope
Project Benefits or Risks
Hockey Stadium Construction Project
$5 Million
Project Lead
Project One Pager

## Slide 3: Project Description
With the current hockey stadium designated as a historical landmark, MSU is building a new, sustainable hockey facility on or near campus. The stadium will align with the university’s “Sustainable Campus” vision, incorporating eco-friendly design, construction, and operations while supporting MSU’s championship legacy.

## Slide 4: Key Features

## Slide 5: Key Features
Separate male/female facilities with bathrooms and TVs.
High-quality rink designed by Everything Ice.
General, VIP, accessible seating with amenities.
High-speed internet, digital scoreboard.
Seating Zone
Ice Rink
Technology
Hockey Stadium
Locker Rooms

## Slide 6: Team Members
Sijan Dahal
Yaman Pandey
Masters of Science in Information Technology
Masters of Science in Manufacturing Enginering Technology
Bachelors of Science in Mechanical Engineering
Bachelors of Science in Information Technology

## Slide 7: Table of contents 01 04 02 03
Project Definition
Project Plan
Project Execution
Project Closure

## Slide 8: Project Definition 01
Goals: Construct a new hockey stadium to replace the unavailable Mayo Clinic Health System Event Center.

## Slide 9: Tasks
Design
Construction
Resource allocation
Testing and Quality Control

## Slide 10: Specifications
200 ft x 85 ft
5,000 People
$50 million
October 2027
Arena Size
Budget
Seating Capacity
Completion Date

## Slide 11: Technical Specifications
Dimensions: 200 ft x 85 ft
Ice Thickness: 1 inch (2.5 cm)
Cooling System: Provided by Everything Ice to maintain 22°F ice temperature
Safety: Protective glasses and barriers for spectators
Lighting: Proper visibility for day and night play.
Size: 20 ft x 10 ft
Resolution: 1920 x 1080 pixels
Real-time Data: Updates for goals, misses, and cards
Ice Rink (NHL Standard)
Scoreboard

## Slide 12: Technical Specifications cont.
NFPA Codes
NFPA 70 (Electrical Wiring)
NFPA 70B (Equipment Maintenance)
NFPA 70E (Electrical Safety)
NFPA 110 (Emergency Power)
  ASHRAE 62 Code: Ventilation for acceptable indoor air quality
Electrical Installments:
(Heating, Ventilation and
Air Conditioning) HVAC

## Slide 13: Milestones and objectives
Nov 2025
Jan. 2026
Dec. 2025
Oct. – Dec. 2026
Design Approval
Ice Rink
Installation
Construction Start
Testing & Handover

## Slide 14: Gantt Chart

## Slide 15: Network Analysis

## Slide 16: Network Analysis

## Slide 17: Network Analysis

## Slide 18: Network Analysis

## Slide 19: Network Analysis

## Slide 20: Project Priority Matrix
 | Time | Scope | Cost
Constrain |  |  | XX
Enhance |  | XX | 
Accept | XX |  | 
Cost is Constrained because it has a fixed budget of $50 million.
The scope is enhanced because the project should exceed expectations.
Time is accepted as it is non-negotiable and should be completed by October 2027

## Slide 21: Responsibility Matrix
Task | Sijan | Yaman
Definition | S | R
Project Plan | R | S
Construction Work | R | S
Mechanical & electrical Work | S | R
IT Infrastructure | R | S
Project closure & Testing | R | S
Legend R == Responsible S == Support

## Slide 22: Project Plan 02

## Slide 23: Schedule
Design Approval
Nov. 2025
Project Handover
Oct 2027
Construction Start
Jan 2026
Grand Opening
Dec. 2027
01
03
02
04

## Slide 24: Budget & Resources
$50 million with a 10% buffer.
Contractors (Everything Ice)
University support teams
Materials
IT infrastructure
Skilled labor
Materials
IT infrastructure.
Budget
Resources
Staffing

## Slide 25: Work Break Down Structure

## Slide 26: Resources
Resource Name | Type | Max. Units in percentage | Std. Rate per Hour in ($)
Civil Engineer | Work | 1200 | 65
Electrical Technician | Work | 800 | 55
HVAC Technician | Work | 600 | 60
Structural Designer | Work | 450 | 70
Legal Advisor | Work | 150 | 120
Project Manager | Work | 250 | 95
Quality Control Inspector | Work | 200 | 50
Plumber | Work | 4000 | 40
Electrician | Work | 3000 | 50

## Slide 27: Project Budget
Budget Category | Estimated Cost (Millions) | Description
Labor Costs | $15 | Skilled workers, contractors, and support staff
Design and Engineering | $5 | Design team, engineering consultancy
Construction Materials | $10 | Building materials for the stadium
Cooling System (Ice Rink) | $6.5 | Equipment from Everything Ice for rink cooling
Scoreboard & Technology | $2.3 | Scoreboard setup and technology integration
Electrical Installations | $3 | Electrical systems for safety and operations
HVAC System | $2 | HVAC system for stadium air quality
Contingency Fund | $3.5 | Buffer for unexpected expenses
Total Budget: $47.3 Million

## Slide 28: Risks Associated with project
Insufficient workers delaying project progress.
Severe conditions halting construction activities.
Delayed materials affecting schedules.
Accidents causing downtime and lawsuits.
Exceeding financial resources and limits.
Last-minute alterations increasing project costs.
Labor shortages
Weather Challenges
Overbudgeting
Late Deliveries
Worker Injuries
Design Changes

## Slide 29: Risk Breakdown Structure

## Slide 30: Risk Severity Table
Green  Low Risk
Yellow  Medium Risk
Red  High Risk
Risk | Likelihood | Impact | Severity | Category
Labor Shortages | 3 | 3 | 9 | High
Design Change | 1 | 2 | 2 | Low
Weather Challenges | 2 | 2 | 4 | Medium
Over Budget | 1 | 2 | 2 | Low
Injury at site | 2 | 3 | 6 | Medium
Equipment late delivery | 1 | 2 | 2 | Low

## Slide 31: Risk Response Development
Risk Event | Response | Contingency Plan | Trigger | Who is Responsible
Equipment Failure | Mitigate: Performing regular maintenance | Making sure the backup equipment is ready | Equipment breakdown | Yaman Pandey
Project Delays | Schedule: Regularly monitoring the project's progress and milestones | Additional human resource | Tasks fall behind the scheduled date | Sijan Dahal
Labor Shortages | Mitigate: Hiring additional staff, Hiring the employee from the staffing company | Hiring contractors and backup employees ready in case someone leaves | All staff occupied; Employees left the work for good | Sijan Dahal
Weather Challenges | Acceptance Monitoring weather regularly, construction work in the summer | Pausing outdoor activities and focusing on indoor works | Extreme weather conditions in MN. Blizzards, Snowstorms | Yaman Pandey
Technology Failure | Mitigate: Patching and updating the software with the help of IT professionals | Backup system and tech support team standby | Failure of Scoreboard | Sijan Dahal
Over Budget | Mitigate: Minoring costs of the project and breaking down budgets | Reducing project scope | When the cost of the project exceeds by 20% | Yaman Pandey
Equipment Delays | Mitigate: Contact the supplier regularly for the logistics | Supply from less than 50 miles i.e. Finding local suppliers | The logistics company delays the shipment | Both

## Slide 32: Project Execution 03

## Slide 33: Resource Allocation – Before Levelling the Slack

## Slide 34: Project Timeline without Levelling the Slack

## Slide 35: Project Timeline After Levelling the Slack

## Slide 36: Status Report

## Slide 37: Changing Working Time In Holidays

## Slide 38: Project Closure Contract

## Slide 39: ProjectAccomplishmet
Project Name: | Mankato Ice Hockey Arena
Governing Body: | Minnesota State University, Mankato
Executive Sponsor: | Minnesota State University, Mankato
Project Manager: | Sijan Dahal & Yaman Pandey
Date: | 12/11/2027
Accomplishment | Details
Mankato Arena Design Completion | The designed was done by Architecture and was approved by MSU.
Permits Secured | The necessary permits to start the construction was approved from blue earth county.
Construction Completion | The Ice Hockey arena was completed on time and within budget of $ 50 million
Operational and IT infrastructure setup | All the infrastructure such as Ice Rink, Cooling System, Digital Scoreboard have been finalized.

## Slide 40: Transfer to Operations
Role | Name | Transition Date
Functional Owner | Yaman Pandey | 10/31/2027
Service Owner | Sijan Dahal | 10/31/2027
Service Manager | Yaman Pandey, Sijan Dahal | 10/31/2027

## Slide 41: Project Execution
Weekly updates for staff, customers, and management.
Mitigating risks with contingency planning.
Standards adhered to (NHL regulations, ASHRAE specifications).
Regular tracking of milestones and resource utilization.
Status Reports
Quality Control
Changes
Forecasts

## Slide 42: Project Closure 04

## Slide 43: Project Closure
Weekly updates for staff, customers, and management.
Mitigating risks with contingency planning.
Gradual handover of equipment and facilities.
Post-project review for lessons learned and feedback collection.
Customer Training
Resource Release
Documentation Transfer
Evaluation

## Slide 44: 2D CAD Model

## Slide 45: Lesson Learned
Cross-functional collaboration is best for project management
Communication gap can cause the project to fail

## Slide 46: THANK YOU
Any Questions?